## Task Tracker
ID | Task Name | Category | Status | Priority | Module | Effort | Description | Due Date
1 | Settings Page Implementation | Feature | Completed | High | Frontend | Large | Created Settings page with audio controls and language selector | 2026-05-15
2 | Multi-Language Support (8 Languages) | Feature | Completed | High | Frontend | Large | Implemented support for 8 Indian languages with native scripts | 2026-05-15
3 | Landing Page 3-Button Layout | Enhancement | Completed | Medium | Frontend | Medium | Optimized button sizing to fit Profile, Settings, Leaderboard | 2026-05-15
4 | Multiplayer Sound Effects | Feature | Completed | Medium | Frontend | Small | Added sound notification when players change ready status | 2026-05-15
5 | Private Lobby Backend Filtering | Feature | Completed | High | Backend | Small | Verified private lobbies filtered at backend, not sent to frontend | 2026-05-15
6 | Translation System Expansion | Enhancement | Completed | High | Frontend | Large | Added 1800+ translation keys for 8 languages | 2026-05-15
7 | Game Name Rebrand (TRUMPFIRE) | Enhancement | Pending | High | Frontend | Medium | Update all references from 'Dehla Pakad Pro' to 'TRUMPFIRE' branding | 2026-05-20
8 | Logo Design for TRUMPFIRE | Design | Pending | High | Design | Large | Create professional logo for TRUMPFIRE game - requires designer | 2026-05-25
9 | Browser Hard Refresh Caching | Bug | Pending | Medium | Frontend | Small | Document/fix dev server hot reload caching issues for translations | 2026-05-17
10 | Test Private Lobby Flow | Testing | Pending | Medium | Frontend/Backend | Small | Test creating private lobby and verify it's not visible in browser | 2026-05-18
11 | Bundle Size Optimization | Performance | Pending | Medium | Frontend | Large | Implement code splitting and dynamic imports to reduce chunk size warnings | 2026-06-15
12 | Sound Customization Settings | Enhancement | Pending | Low | Frontend | Medium | Add individual sound toggle options for different game events | 2026-06-20
13 | Analytics Implementation | Feature | Pending | Medium | Frontend/Backend | Large | Implement game analytics, player stats tracking, and telemetry | 2026-07-01
14 | Mobile App Version | Feature | Pending | Medium | Mobile | Very Large | Create native mobile app versions (iOS/Android) using React Native | 2026-08-01
15 | Push Notifications | Feature | Pending | Low | Backend | Medium | Implement push notifications for game invites and ready status | 2026-07-15
16 | Social Features | Feature | Pending | Low | Frontend/Backend | Large | Add friend system, messaging, and social profile features | 2026-08-15
17 | Advanced Game Statistics | Feature | Pending | Low | Frontend/Backend | Medium | Add detailed game history, win rate, card statistics per player | 2026-07-30
18 | Admin Dashboard | Feature | Pending | Low | Frontend/Backend | Large | Create admin panel for game management, user moderation, analytics | 2026-09-01
19 | Automated Testing Suite | Testing | Pending | High | Frontend/Backend | Large | Implement comprehensive unit and integration tests with CI/CD | 2026-06-30
20 | Performance Monitoring | Feature | Pending | Medium | Frontend/Backend | Medium | Set up APM monitoring, error tracking, and performance metrics | 2026-07-15
21 | 5 Sound Themes System | Feature | Completed | High | Frontend | Large | Created 5 distinct sound themes (Classic, Modern, Nature, Magical, Cyberpunk) with theme selector in Settings | 2026-05-15